## Sheet1
| Date | Objective | Details | Varun Comments
Week 1 | 2019-08-19 | Create schema and databases | This will require me to look into setting up some graph databases
Week 2 | 2019-08-26 | Write scripts for data collection using API and web scraping | Once my data collection tools are built I will likely create a cron job to collect as much data as the API allows daily
Week 3 | 2019-09-02 | Research NLP and create plan on how to use it for classification | Look for models, libraries, that can be used for NLP. Also there are a lot of papers on this NLP for political classification that I will need to get familiar with
Week 4 | 2019-09-09 | Use and test NLP models
Week 5 | 2019-09-16
Week 6 | 2019-09-23 | Research graphing techniques for classification | I have a feeling perhaps this should come before the creation of schema and databases. We can discuss this.
Week 7 | 2019-09-30 | Implement/testing graphing techniques for classification
Week 8 | 2019-10-07
Week 9 | 2019-10-14 | Use the combination of graph analysis and NLP to create a scoring metric for polarization
Week 10 | 2019-10-21 | Start planning web app for serving insights on tweets
Week 11 | 2019-10-28 | Build backend for web app
Week 12 | 2019-11-04
Week 13 | 2019-11-11 | build front end for web app
Week 14 | 2019-11-18
Week 15 | 2019-11-25 | tbd | I imagine there will be unseen delays that will push things back. I'll have about 3 weeks left to account for this. Please comment if this is reasonable
Week 16 | 2019-12-02 | tbd
Week 17 | 2019-12-09 | tbd
Week 18 | 2019-12-16 | tbd